## Slide 1: CNG P3 Project Update January 2017 PPTA Winter Meeting
Notes: Bob

## Slide 2: Overview
General Project Update
Current and Future Activities
Design and Construction Cycle
Gas and Electric Utilities
TAA
Notes: Scott

## Slide 3: PennDOT P3 Team
CNG P3
Program Manager
Scott Zeevaart
PennDOT, BPT
Bob Sharp
PennDOT, P3 Office
PennDOT, BPT
Nick Baldwin
Sam Plocinski
Trillium Project Manager
Guido Struyk
Trillium Design Team
Trillium Construction Team
Trillium O&M Team
Program and Construction Management Team
Scott Schriner
Tim King
Brett Brenize
Mike MacAllister
Transit Agencies
Notes: Scott

## Slide 4: 2016 Activities
Site Visits
  Surveys, Geo-Tech, TA meetings
Design Coordination and Approvals
  % complete review meetings
  Site design field amendments
Permitting – AHJs
Notice to Proceed 1 – Achieved 10/26/2016
Notice to Proceed 2 - (Site Specific)
Notes: Scott

## Slide 5: 2017 Construction Initiation
Underway:
  CAMTRAN-Johnstown
Near Term Initiation Q1 2017
  CPTA – York
  MMVTA – Donora
  WCTA-Greensburg
  CATA-State College
Notes: Scott

## Slide 6: CAMTRAN – Johnstown Renderings
Notes: Scott

## Slide 7: CAMTRAN-Johnstown 1/4/2017
Notes: Scott

## Slide 8: General Overview of Activities
Initial Site Visit
Design Coordination – 120+ days
Utility Coordination 150+ days
Permits – 100 days
Construction – 70-80 days
Commissioning – 14 days
Throughput Testing – 14 days
CNG Readiness
Notes: Guido

## Slide 9: On-Going Activities
Design and Permitting Underway for 16 Sites
  Building and Maintenance Facility Modifications
  Fueling Station Plans
Q1 2017
  7 sites will be under construction
2017 – Target 12 CNG stations will be fully operational
Utility infrastructure design and upgrades
  Long lead times
CNG Readiness Compliance Activities
Notes: Guido

## Slide 10: Utilities Overview
Trillium’s Responsibility - Distribution
  Gas Infrastructure upgrades
    Design and Routing – Gas Provider
    Applicable $$ upgrades – Trillium
    LEA – TA will need to execute with Guidance from Project Team
  Electrical Infrastructure upgrades
    Design and Routing – Electrical Provider
    Applicable $$ upgrades – Trillium
    LEA – TA will need to execute with Guidance from Project Team
Notes: Guido

## Slide 11: Utilities Overview
TA’s Responsibility – Commodity
  TA is required to procure commodity supply with a natural gas provider
  Needed in time for commissioning, approximately 8 weeks prior to CNG Readiness
Notes: Guido

## Slide 12: Operations and Maintenance (O&M)
O&M Webinar overview
  February 2nd at 10:30 a.m.
Webex invitation to be sent to TAs and PPTA early next week
Opportunity to understand Trillium and TAs responsibility with regards to O&M
Hosted by PennDOT – Trillium Presenter
Be prepared to ask Questions
Notes: Guido

## Slide 13: Forthcoming Training
Basic Station Operation
Fueling
Defueling
Emergency Response
On-going Training
  Annual Refresher
  New Employees
  Site-Specific Modifications
Notes: Guido

## Slide 14: TAA Update
TAA – Version 3 was sent out 1/10/17
  17 Sent Out
Forthcoming Amendment regarding Turnback
RTKL Clauses
Notes: Scott
Delays:
Due to change at OGC.
Questioning format of many other PennDOT Contracts, not just the TAAs.
Recently two minor issues have been identified with the TAAs that were at the OGC
Working to resolve
I will be in touch with the Transit Agencies that have already submitted a TAA once we resolve the issues with OGC.
Amendment
Are currently working with PennDOT Office of Chief Counsel to draft the language to clarify with the Transit Agencies what happens to the CNG Fueling Station at the end of the Term.
RTKL
TAA, Section 10.12 intent to not restrict the normal operations/business of the Transit Agencies.
You are able to discuss the P3 project for your site during the various public meetings that are occurring.
Obviously for more detailed questions about the project as a whole, we would ask that you refer the inquiry to the PennDOT Press Office.
In addition, the goal of 10.12 is to make sure that no press releases or public interviews are initiated without coordination from PennDOT in order that we provide consistent messaging.
If you receive a RTK request for information regarding the CNG P3 project, please remember to coordinate with PennDOT so that PennDOT’s RTK Office can be involved.

## Slide 15: Contact Information
Any Questions regarding the CNG P3 Project, please contact either:
Scott Zeevaart
  (717) 877-2644
  szeevaart@gfnet.com
Bob Sharp
  (717) 783-9461
  rosharp@pa.gov
Notes: Scott